## DO NOT DELETE
This template is an exclusive property of Mapua-Malayan Digital College and is protected under Republic Act No. 8293, also known as the Intellectual Property Code of the Philippines (IP Code). It is provided solely for educational purposes within this course. Students may use this template to complete their tasks but may not modify, distribute, sell, upload, or claim ownership of the template itself. Such actions constitute copyright infringement under Sections 172, 177, and 216 of the IP Code and may result in legal consequences. Unauthorized use beyond this course may result in legal or academic consequences. Additionally, students must comply with the Mapua-Malayan Digital College Student Handbook, particularly with the following provisions: * Offenses Related to MMDC IT: - Section 6.2 – Unauthorized copying of files - Section 6.8 – Extraction of protected, copyrighted, and/or confidential information by electronic means using MMDC IT infrastructure * Offenses Related to MMDC Admin, IT, and Operations: - Section 4.5 – Unauthorized collection or extraction of money, checks, or other instruments of monetary equivalent in connection with matters pertaining to MMDC Violations of these policies may result in disciplinary actions ranging from suspension to dismissal, in accordance with the Student Handbook. For permissions or inquiries, please contact MMDC-ISD at isd@mmdc.mcl.edu.ph.

## Effort Estimation
MO-IT101 - Computer Programming 1
Effort Estimation
GUIDE QUESTION | TASK | RESPONSE
What are the main tasks you need to do? (Insert additional rows if you have more than 10 tasks) | 1 | Visualization of our requirements
| 2 | Employee details presentation
| 3 | Hours worked calculation
| 4 | Create repository
| 5 | Testing and revision
6
7
8
9
10
What do you need to know to accomplish these tasks? (Insert additional rows if you have more than 10 tasks) | 1 | Review MotorPH Requirements
| 2 | Create Use Case Diagram and Wireframe that was easy to understand
| 3 | Collaborate and discussion with groupmates
| 4 | Identify missing or incorrect details
5
6
7
8
9
10
What additional help do you think you need to be able to do each task? (Insert additional rows if you have more than 10 tasks) | 1 | Guidance on proper screen flow and layout
| 2 | Feedback from mentor or teammates on design clarity
| 3 | Groupmates meetings for some clarification for the output and tasks
4
5
6
7
8
9
10
Given the nature of the task, the knowledge you need, and any additional help you need, how long do you think it would it take you (in hours) to finish each task? (Insert additional rows if you have more than 10 tasks) | 1 | For the Main task # 1, estimated per week in total of 6 hours
| 2 | For the Main task # 2, estimated per week in total of 10 hours
| 3 | For the Main task # 3, estimated per week in total of 6 hours
| 4 | For the Main task # 4, estimated per week in total of 2 hours
| 5 | For the Main task # 5, estimated per week in total of 4 hours
| 6 | For the Main task # 6, estimated per week in total of hours
7
8
9
10
In this course, you are expected to dedicate 7.5 hours per week. Based on the total number of hours you estimated, how many weeks will you need to finish your outputs? | 12 weeks

## Project Plan Guide
MO-IT101 - Computer Programming 1
Project Plan Guide
Use the guide below to help you fill out this template
1 | Begin by filling out the general information section above.
2 | TASK # - Use whole numbers to specify main tasks (e.g., 1,2,3). If the task is considered a sub-task, advance the numbering using decimal points to still identify what the main task is (e.g., 1.1, 1.2, 1.3).
3 | TASK - Describe the task. Start tasks with verbs/action words to add specificity, e.g., List requirements instead of simply Requirements.
4 | DEPENDENCY - Identify the task which cannot be started unless a previous task has been completed. Leave this blank if there is no dependency.
5 | OWNER - Identify the person responsible for completing the task.
6 | START DATE & END DATE - Identify the planned start and end dates per task. The main task's start and end-date should be the start date of the first sub-task and the end date of the last sub-task. The last end date in your project plan should be within the submission dates indicated in your syllabus.
7 | STATUS - By default, all tasks start with a Not Started status. Change the status to In Progress if it's already being worked on and Completed once the task is done.
8 | ACTUAL START & END DATE - Specify the actual start and end dates per task. This allows you to identify whether you were able to adhere to your initial timelines and if you will be able to complete the rest of your tasks on time. If you see that you don't have sufficient time, you need to work with your team to decide on alternatives or adjustments.
9 | NOTES - Indicate any notes or reminders you may have for each task.

## Project Plan
MO-IT101 - Computer Programming 1
Project Plan
TASK # | TASK | DEPENDENCY | OWNER | START DATE | END DATE | Estimated Effort (hrs) | STATUS | ACTUAL START DATE | ACTUAL END DATE | NOTES
1 | Visualization of Requirements |  | Group 13 |  |  | 6 | Completed |  |  | Overall scope review
1.1 | Requirements gathering |  | Group 13 | 2026-01-23 | 2026-02-09 | 4 | Completed | 2026-01-25 | 2026-02-08
1.2 | Creation of Use Case Diagram | 1.1 | Group 13 | 2026-01-28 | 2026-01-30 | 6 | Completed | 2026-01-28 | 2026-02-08
1.3 | Creation of Wireframe | 1.2 | Group 13 | 2026-02-04 | 2026-02-06 | 4 | Completed | 2026-01-28 | 2026-02-08
2 | Employee details presentation |  | Group 13 |  |  |  | Completed
3 | Hours worked calculation |  | Group 13 | 2026-02-09 | 2026-02-15 | 6 | Completed | 2026-02-09 | 2026-02-15
3.1 | Compute Semi-Monthly Salary Based on Hours Worked |  | Group 13 | 2026-02-16 | 2026-02-22 | 6 | Completed | 2026-02-17 | 2026-02-22
3.2 | Apply government deductions |  | Group 13 | 2026-02-24 | 2026-02-28 |  | Completed | 2026-03-03 | 2026-03-03
4 | Create repository |  | Group 13 | 2026-03-08 | 2026-03-08 | 2 | Completed | 2026-03-08 | 2026-03-08
4.1 | Upload Java files in repository |  | Group 13 | 2026-03-08 | 2026-03-09 | 0.5 | Completed | 2026-03-11 | 2026-03-11
5 | Testing and revision |  | Group 13 | 2026-03-10 | 2026-03-13 | 4 | Completed | 2026-03-11 | 2026-03-16
5.1 | QA testing |  | Group 13 | 2026-03-14 | 2026-03-16 | 1 | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started